## Project Plan
BlackBelt Project Tracker and Weekly Gantt Plan | [15 empty] | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan
PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE
Project Title | BlackBelt MVP v0.1.0 |  |  | Project Manager |  |  |  | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | COMPLETE | COMPLETE | COMPLETE | COMPLETE | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | AT RISK | AT RISK | AT RISK | AT RISK | P0 TASKS | P0 TASKS | P0 TASKS | P0 TASKS
Company Name | BlackBelt |  |  | Timeline Start |  | 2026-07-10 |  | 30 |  |  |  | 2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 30
WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW
Workstream | Task | Owner | Status | Priority | Start Date | End Date | Days | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20
Foundation | Frontend scaffold |  | Complete | P0
Foundation | Backend scaffold |  | Complete | P0
Foundation | Connect Supabase project |  | Not Started | P0
Foundation | Provision Railway PostgreSQL |  | Not Started | P0
Foundation | Run initial Prisma migration |  | Not Started | P0
Foundation | Implement Supabase JWT validation |  | Not Started | P0
Authentication | Registration and login |  | Not Started | P0
Authentication | Session persistence |  | Not Started | P0
Authentication | Logout and password reset |  | Not Started | P0
Onboarding | Role selection splash |  | Not Started | P0
Onboarding | Owner onboarding |  | Not Started | P0
Onboarding | Student invite onboarding |  | Not Started | P0
Onboarding | Role-based completion redirect |  | Not Started | P0
Academy | Create academy and unique invite code |  | Not Started | P0
Academy | Display and share invite code |  | Not Started | P0
Academy | Student roster |  | Not Started | P0
Academy | Professor role management |  | Not Started | P0
Schedule | Create recurring class |  | Not Started | P0
Schedule | Edit or deactivate class |  | Not Started | P0
Schedule | Weekly schedule view |  | Not Started | P0
Check-in | Student requests check-in |  | Not Started | P0
Check-in | Pending review list |  | Not Started | P0
Check-in | Approve or reject with self-approval guard |  | Not Started | P0
Check-in | Count approved check-in toward progress |  | Not Started | P0
Belt | Student progress view (X/24) |  | Not Started | P0
Belt | Authorized manual promotion |  | Not Started | P0
Belt | Belt change history and audit trail |  | Not Started | P0
Dashboards | Student dashboard |  | Not Started | P0
Dashboards | Owner dashboard |  | Not Started | P0
Membership | Plan creation, assignment, and status |  | Not Started | P0
Source: current-handoff.md and 06-current-roadmap.md. P0 reflects required v0.1 scope. Owners and task dates remain blank where undocumented; Timeline Start is the tracker creation date and only anchors the 20-week view. Edit task dates to activate Gantt bars.